## Sheet1
| JOB INFORMATION | [7 empty] | ACTUAL COSTS |  |  |  |  | ESTIMATED REMAINING COSTS |  |  |  |  | PROJECTED COSTS | ESTIMATED / PLANNED COSTS |  |  |  |  | COST DELTA
Job # | Job Cmpl? | Job Closed? | Order | Part # | Prod. Qty | # Last Cmpl Op Qty | Last Cmpl Asm # | Last Cmpl Opr # | Actual Total (sum of column K+L+M+N) | Actual Mtl | Actual Labor | Actual Burden | Actual Subcontract | Estimated Cost for Remaining Operations (aka Planned Cost for remaining Ops) | Remaining Mtl | Remaining Labor | Remaining Burden | Remaining Subcontract | Projected Cost (sum column J + column O) | Estimated Total (aka Planned cost) | Planned Mtl | Planned Labor | Planned Burden | Planned Subcontract | Delta (Estimated - (Actual + Remaining)) or (Planned - Projected) | Delta Mtl | Delta Labor | Delta Burden | Delta Subcontract

## Sheet2
For remaining Operations on Job # 000023597
|  | CREW SIZE | EST. HOURS | RATE | PLANNED COST (EPICOR REFERS TO THIS AS "ESTIMATED") | Est. Prod Hours | Est. Burden Cost
Opr: 190 | GHELP | 1 | 0.5 | 30 | 15 | 0.5 | 123.2
Opr: 191 | IPIN | 1 | 0 | 30 | 0 | 0 | 0
Opr: 192 | GHELP | 1 | 0 | 30 | 0 | 0 | 0
Opr: 193 | SPIN2 | 1 | 0 | 38 | 0 | 0 | 0
Opr: 194 | SPIN2 | 1 | 0 | 38 | 0 | 0 | 0
Opr: 195 | SPIN2 | 1 | 0 | 38 | 0 | 0 | 0
Opr: 196 | SPIN2 | 1 | 0 | 38 | 0 | 0 | 0
Opr: 197 | SPIN2 | 1 | 0 | 38 | 0 | 0 | 0
Opr: 198 | SPIN2 | 1 | 0 | 38 | 0 | 0 | 0
Opr: 199 | IPIN | 1 | 0 | 30 | 0 | 0 | 0
Opr: 200 | IPIN | 1 | 0 | 30 | 0 | 0 | 0
Opr: 201 | GHELP | 1 | 0 | 30 | 0 | 0 | 0
Opr: 205 | IPIN | 1 | 0.5 | 30 | 15 | 0.5 | 123.2
Opr: 210 | IPIN | 1 | 1 | 30 | 30 | 1 | 246.4
Opr: 220 | DATA | 1 | 0.5 | 30 | 15 | 0.5 | 123.2
Opr: 230 | DATA | 1 | 0.5 | 30 | 15 | 0.5 | 123.2
|  |  |  | TOTAL: | 90 |  | 739.2